## Slide 1: Pocket Chef Retrospective
By PocketChef.Inc

## Slide 2: Backlog
Automated test
Remote Database
tests
Manual test
Camera Access
Local database
Input and retrieval
Appealing GUI
Image Recog Research
Card View
Send recipes to server
redesign the upload screen

## Slide 3
Ricardo
Jacob
Linh
Kyle
Jhamon
Automated test
Remote Database
tests
Camera Access
Local database
Input and retrieval
Appealing GUI
Image Recog Research
Card View
Send recipes to server
redesign the upload screen
Card View
Manual test
Local database
Input and retrieval

## Slide 4
Ricardo
Jacob
Linh
Kyle
Jhamon
Automated test
Remote Database
tests
Local database
Input and retrieval
Manual test
Camera Access
Local database
Input and retrieval
Image Recog Research
Appealing GUI
Send recipes to server
redesign the upload screen
Card View
Card View

## Slide 5: How were standups held?
Date | Discussed | Status
February 5 | * Manual testing programs through Espresso * Uploading recipes to the remote database from phone | Complete Complete
February 8 | * Github automated testing program * Remote database testing program | Complete Complete
February 10 | * Bug fixes * Configuring local database * Reformatting upload form | Complete Complete Complete
February 12 | * Card view layout * GUI appearance | Complete Incomplete
February 22 | * Accessing camera * Sprint deliverable | Incomplete Complete

## Slide 6: Github Commits
Object | Total
Commits | 76
Merges | 20
Pull requests | 16
Note: We are still having issues with our Github. Every member did contribute even if not displayed in the graph

## Slide 7: Sprint Velocity
Chart: Burndown Chart-Sprint 2
| 44232 | 44235 | 44237 | 44239 | 44242 | 44244 | 44246 | 44249 | 44251
Expected remaining hours | 166.5 | 148 | 129.5 | 111 | 92.5 | 74 | 55.5 | 37 | 18.5 | 0
Actual remaining hours | 166.5 | 165 | 152 | 130.5 | 117 | 97 | 80 | 38 | 18 | 10

## Slide 8: What We Learned
How to configure automated tests in Github through Github actions
How to configure behavior tests through Espresso
How to configure remote server infrastructure tests
How to store items locally on the device
How to design and layout fragments
How to connect data between fragments
How to design and operate the recycler and card view
How to upload and retrieve data from the remote database

## Slide 9: What we will do next sprint
Figure out how to properly manage the contributions graph on github
Access the camera
Add functionality to the cards
Implement a card view to both the generate and pantry
Begin designing the image recognition system
Research the limitations of remote databases
Research and manage the resources (battery, memory, etc)